## Slide 1
Improving NPT / Flat Time
as a Drilling Contractor

## Slide 2: Outline
Introduction
How to approach “reduce NPT/Flat time”
  Identification of areas to improve
  How can they be improved?
  Examples of time savings
Improvements in today’s market
  How to look at savings differently
Conclusion

## Slide 3
As contractors, we are constantly looking for ways to reduce our well cycle time to be competitive. With the current market especially, we must strive to reduce times on the items we control:
NPT/Flat time

## Slide 4: Reducing NPT/Flat Time
Two perspectives exist in today’s market:
  Overall time reduction of flat time / NPT
    Remove limitations
    Define processes
    Reduce critical path operations
    Standardization of human inputs
    Remove the unknowns
  Improvements to fit the market
    Eliminate cost with changes in time / work
    Cost benefits versus time

## Slide 5: Potential Areas of Improvement
Rig Moves
  Limitations in our Processes
  Any Lesson’s Learned?
Nipple Up / Test
  Critical Path Flat time
Drilling / Tripping Connections
  High Impact on Overall Well Cycle Time
Unexpected Events
  Mud Pump Expendables

## Slide 6: Improvement Areas – Rig Moves
Initially Identified Areas
1. Limited by daylight hours
  Implemented use of 24 hrs slowly
2. Better planning for all circumstances
  Created plans based on release time
3. Better communication of all involved
  Rig Move Prep Meetings
  After Action Reviews
*9 Months Implementation
*4 Months Implementation
*2 Months Implementation

## Slide 7: Improvement Areas – Rig Moves
Fine Tuning
Improvements
1. Looking at the use of Crews
  Better planning / usage
2. Plan for the unexpected
  Maintenance / Audits
  Better prep meetings
3. Train for the future
Extra Crew Members

## Slide 8: Improvement Areas – Nipple Up
Current Critical Path
Install well head -> Skid to next well -> Nipple Up BOP ≈ 8-10 hours
How can we remove this from the critical path
or improve the critical path…
SIMOPs

## Slide 9: Improvement Areas – Nipple Up
New Critical Path
Skid to the next well < ≈ 6-8 hours
  *Better planning of our business helps us utilize the same number of crews but reduce overall hours
Notes: Coordinate with operator on well centers up to 22 – stop mid skid to lower chain falls – coordinate with nipple up crews to bring two individuals with two torque wrenchs

## Slide 10: Improvement Areas – Connections
Standardizing interactions with the system:
What are we doing different between rigs?
What makes one connection better than another?
What can we control and what can we not?
Measure
Implement
Improve

## Slide 11: Improvement Areas – Other
Planning for the Expected
& the Unexpected
Mud Pump Expendables: We know they will not last but can we predict when they will fail?
Using our data and planning ahead can be an easy solution with tremendous results

## Slide 12
How does today’s market affect these initiatives?

## Slide 13: Improving in Today’s Market
Rig Moves
  Improvement Requirements:
    Added extra crews
    Added extra trucks
  Current Considerations:
    Where / when do we need extra crews & trucks?
      Utilizing 1 extra crew & extra trucks 2 days
*Numbers above are arbitrary and reflect cost % comparison & do not reflect true actual cost

## Slide 14: Improving in Today’s Market
Rig Utilization
  Potential Batch Drilling Savings
    Fewer times laying down pipe
    Few mud changes / pit cleanings
    End back @ home position for improved move times
  Potential Sequential Drilling Savings
    Few instances of Nipple Up / Test BOP
    Can utilize SIMOPs for Nipple Up
    So initially what would you say is the best option?

## Slide 15: Improving in Today’s Market
Looking at time and cost you get a different picture:
- Coordinating our planning can save both time and money which is essential in this market.
*Numbers above are arbitrary and reflect cost % comparison & do not reflect true actual cost
Notes: Assuming 3 string well

## Slide 16: Conclusion
Decreasing NPT / Flat time
  Looking into a single activity can lead to inefficiencies in other areas
  Systematic approach helps improve efficiencies with the least amount of effort & helps define success/failure
  All around better communication and group efforts in planning and review makes the biggest difference
Looking at time savings from a cost perspective
  Spending more can be more cost effective
  The intuitive answer may not be the logical path in today’s conditions
And….

## Slide 17: Conclusion
Small changes can make vast improvements from both perspectives

## Slide 18
Questions?